## Slide 1
Weekly letter w. 42
HR Core Information flow

## Slide 2
Definition of Green / Yellow / Red Track
Green Track: Ready at MainGoLive
Yellow Track: Ready after MainGoLive (mitigation will be set in place temporarily)
Red Track: Out of scope completely (mitigation will be set in place permanently)

## Slide 3
Bug fix - go-live critical errors Green Track (or critical publishing side)
Build Green Track
Bug fix - non-go-live critical Green Track
Build Yellow Track
Bug-fix after “MainGoLive” bugs (involve redesign and rework)
Build consumer prio 2
Build consumer prio 3
Red Track not to be developed/tested
General prioritization of activities

## Slide 4
Activities scheduled
Status w. 42
Solution Architects
Define | Start date | Target date
Totara |  | 8/7
Peakon | 2/9 | 20/10
Synergi | 1/9 | 12/9
Design | Start date | Target date
Ramp Totara | 4/8 | 27/11
Adapter Peakon TBD | 16/9 | 7/11
Ramp Peakon | 16/9 | 7/11
Ramp Carsmart | 15/9 | 27/10
Ramp Synergi | 13/10 | 24/10
Responsible SA | System
Per Anders Jørgensen | ProMark NO, HRM, DK Middleman, Mepco, Coolpro
Patrik Vesth | BR, C7, Billy, Benify
Jan Nielsen Damlund | Unit4, Carsmart
Oscar Sjödén | Unit4, Billy
Mats Sjöström | TEM, Totara, Peakon, Synergi
Simon Boman | SuccessFactor
Tobias Stein | ClearSkye
Integration Request | Start date | Target date
Peakon | 4/8 | 1/9
Synergi | 11/8 | 29/8

## Slide 5
Status w. 42
NCIP team
Development | Start date | Target date
SuccessFactors-EmployeeCountryEmployeeNumberUpdated-Sub | 20/10 | 28/10
Development | Start date | Target date
Prio 2 consumers ↓ |  | 
TEM-Employee2409-Sub | 24/9 | 21/10
TEM-Employee2409WithBankAccount-Sub | 24/9 | 21/10
TEM-Identity2409-Sub | 24/9 | 21/10
Totara-Employee2409CurrentlyEffective-Sub | 25/9 | 6/11
Carsmart-Employee2409CE-Sub | 28/10 | 18/11
Carsmart-EmploymentTerminated-Sub | 28/10 | 18/11
Billy-Employee2409CurrentlyEffective-Sub | 27/10 | 17/11
Billy-Identity2409-Sub | 18/11 | 1/12
Coolpro-Employee2409CurrentlyEffective | 20/11 | 10/11
Activities scheduled
Green Track
Yellow Track
Red Track
Design | Start date | Target date
Design Totara Ramp | 4/8 | 27/11
Design Carsmart Ramp | 14/10 | 27/10
Design Peakon Ramp | 21/10 | 7/11
Ramp Synergi | 13/10 | 24/10

## Slide 6
Status w. 42
Adapter team
Development | Start date | Target date
Peakon Adapter? | TBD | 
DK Middleman UC: GCH integration file – INM | 20/10 | 10/11
DK Middleman UC: Change of Compensation WCW | 20/10 | 10/11
DK Middleman UC: Hire (new foreign manager) | 20/10 | 10/11
DK Middleman UC: Change of formal manager (foreign) | 20/10 | 10/11
DK Middleman UC: GCH integration file – IDC | 20/10 | 10/11
DK Middleman UC: FrontAvenue integration | 20/10 | 10/11
Design | Start date | Target date
Design Adapter Peakon (TBD if adapter is needed) | TBD | 
Design DK Middleman UC Yellow Track: GCH integration file - INM Change of Compensation WCW Hire (new foreign manager) Change of formal manager (foreign) GCH integration file – IDC FrontAvenue integration | 6/10 | 17/10
Activities scheduled
Green Track
Yellow Track
Red Track

## Slide 7
Status w. 42
SIT test team
Test | Start date | Target date
Unit4 Adapter: Hire, Termination, Rehire, (Identity), Employee2409WithBankAccount | In progress | 
DK Middleman Adapter | In progress | 
Mepco: EmploymentTerminated2409 |  | 23/9
Mepco: Compensation |  | 19/9
Mepco: EmployeeRehired | In progress | 
Mepco: Identity2409 |  | 19/9
Activities scheduled
Green Track
Yellow Track
Red Track
Test | Start date | Target date
Prio 2 consumers ↓ |  | 
Benify: Employee2409CurrentlyEffective | Ready to test | 10/11
Benify: Compensation | Ready to test | 10/11
TEM-Employee2409-Sub | 27/10 | 10/11
TEM-Employee2409WithBankAccount-Sub | 27/10 | 10/11
TEM-Identity2409-Sub | 27/10 | 10/11
C7: Identity2409 | Ready to test | 10/11
C7: Employee2409CurrentlyEffective | Ready to test | 10/11
Ramp DK Middleman: EmployeeCountryEmployeeNumberUpdated-Pub | 20/10 | 28/10
Adapter DK Middleman: EmployeeCountryEmployeeNumberUpdated-Pub | Ready to test | 27/10
SF: EmployeeCountryEmployeeNumberUpdated-Sub | 29/10 | 7/11

## Slide 8
Status w. 42
Gross list of open bugs
https://nccdevelopment.visualstudio.com/Development%20and%20IT/_queries/query/?tempQueryId=dd2ad1b3-5fae-44f3-9c64-1d50ba195419

## Slide 9
Dashboard view of new and active bugs w. 42
The chart tracks the bug status, showing Active Bug trends by State. States included in this view is: Active, New & Resolved.
2025-10-10:
Active (incl dep to test, dev, code review): 14
New: 1
Resolved: 2
Closed: 260
2025-10-17:
Active (incl dep to test, dev, code review): 25
New: 4
Resolved: 8
Closed: 272
Peak due to opening up ”AfterGoLive” bugs

## Slide 10
E2E progress per consumer w. 42
ProMark NO
Test cases
 | Pass | Blocked | Fail | Not Run | N/A
Coverage | 62% | 0% | 23% | 16% | 0%
N/A = test cases not applicable to consumer
Chart: ProMark NO
| w. 34 | w. 35 | w. 36 | w. 37 | w. 38 | w. 39 | w. 40 | w. 41 | end of w. 41
Pass | 60 | 78 | 88 | 90 | 100 | 82 | 82 | 97 | 101
Blocked | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fail | 30 | 30 | 31 | 31 | 30 | 31 | 29 | 40 | 37
Not Run | 44 | 44 | 42 | 40 | 31 | 23 | 29 | 26 | 26
N/A | 0 | 0 | 0 | 0 | 0 | 54 | 54

## Slide 11
E2E progress per consumer w. 42
Unit4
Test cases
 | Pass | Blocked | Fail | Not Run | N/A
Coverage | 91% | 0% | 3% | 6% | <0,5%
N/A = test cases not applicable to consumer
Chart: Unit4
| w. 34 | w. 35 | w. 36 | w. 37 | w. 38 | w. 39 | w. 40 | w. 41 | end of w. 41
Pass | 28 | 43 | 62 | 67 | 76 | 165 | 166 | 183 | 194
Blocked | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fail | 28 | 33 | 36 | 45 | 44 | 13 | 13 | 21 | 7
Not Run | 42 | 38 | 30 | 23 | 23 | 11 | 14 | 14 | 13
N/A | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1

## Slide 12
E2E progress per consumer w. 42
HRM
Test cases
 | Pass | Blocked | Fail | Not Run
Coverage | 83% | 0% | 16,5% | 0,5%
Chart: HRM
| w. 34 | w. 35 | w. 36 | w. 37 | w. 38 | w. 39 | w. 40 | w. 41 | end of w. 41
Pass | 0 | 8 | 34 | 37 | 63 | 92 | 105 | 147 | 166
Blocked | 0 | 21 | 21 | 26 | 0 | 3 | 3 | 0 | 0
Fail | 0 | 39 | 39 | 19 | 7 | 26 | 42 | 49 | 33
Not Run | 0 | 131 | 142 | 143 | 129 | 81 | 53 | 5 | 1

## Slide 13
E2E progress per consumer w. 42
DK Middleman (ProMark DK and EPOS)
Test cases
 | Pass | Blocked | Fail | Not Run
Coverage | 42% | 0% | 11% | 48%
Test cases
 | Pass | Blocked | Fail | Not Run
Coverage | 56% | 0% | 21% | 22%
Chart: ProMark DK
| W. 38 | w. 39 | w. 40 | w. 41 | end of w. 41
Pass | 0 | 7 | 27 | 42 | 51
Blocked | 0 | 0 | 0 | 0 | 0
Fail | 0 | 8 | 8 | 12 | 13
Not run | 0 | 54 | 47 | 47 | 58
Chart: EPOS
| W. 38 | w. 39 | w. 40 | w.41 | end of w. 41
Pass | 0 | 21 | 33 | 57 | 69
Blocked | 0 | 0 | 0 | 0 | 0
Fail | 0 | 8 | 12 | 21 | 26
Not run | 0 | 40 | 45 | 23 | 27

## Slide 14
E2E progress per consumer w. 42
Mepco
Test cases
 | Pass | Blocked | Fail | Not Run
Coverage | 1,5% | 14% | 12% | 78%
Chart: Mepco
| w. 37 | w. 38 | w. 39 | w. 40 | w.41 | end of w. 41
Pass | 0 | 3 | 0 | 0 | 0 | 1
Blocked | 0 | 0 | 0 | 6 | 11 | 9
Fail | 0 | 3 | 8 | 8 | 7 | 8
Not run | 0 | 35 | 68 | 49 | 49 | 48

## Slide 15
Additional activities?
Activity | Start date | Target date
Additional activities
Missing an activity you are working on in the previous lists? Feel free to add the activity here